## Project overview
Field | Value
Project Name | Website Development Project
Project Manager | Devika Sharma
Client Name | ABC Retail Pvt Ltd
Project Start Date | 2025-01-01
Project End Date | 2025-03-31
Total Budget (£) | 25000
Project Status | In Progress
Project Description | Development of a responsive business website including design, development, testing, and deployment
Last Updated On | 2025-02-15

## Task List & Gantt Chart
Task ID | Task Name | Task Description | Phase |  |  | Action/Issue | Start Date | End Date | Status | Comments
T001 | Requirement Gathering | Collect client requirements and expectations | Planning |  |  | Action | 2025-01-01 | 2025-01-07 | Completed
T002 | Project Planning | Create project plan and timeline | Planning |  |  | Action | 2025-01-08 | 2025-01-12 | Completed
T003 | UI/UX Design | Design wireframes and visual layouts | Execution |  |  |  | 2025-01-13 | 2025-01-25 | Completed
T004 | Frontend Development | Develop website frontend using HTML/CSS | Execution |  |  |  | 2025-01-26 | 2025-02-15 | In Progress
T005 | Backend Development | Develop backend and database | Execution |  |  |  | 2025-02-01 | 2025-02-28 | In Progress
T006 | Testing | Perform functional and usability testing | Planning |  |  | Issue | 2025-03-01 | 2025-03-15 | Not Started
T007 | Deployment | Deploy website to live server | Close |  |  |  | 2025-03-20 | 2025-03-25 | Not Started
T008 | Content Creation | Create website content for all pages | Execution |  |  |  | 2025-02-10 | 2025-03-05 | In Progress
T009 | Image & Media Collection | Collect and optimize images and media | Execution |  |  | Dependency | 2025-02-12 | 2025-02-28 | In Progress
T010 | SEO Setup | Configure basic SEO settings | Execution |  |  |  | 2025-03-05 | 2025-03-12 | Not started
T011 | Performance Optimization | Optimize website loading speed | Testing |  |  |  | 2025-03-10 | 2025-03-18 | Not Started
T012 | Cross-Browser Testing | Test website on different browsers | Testing |  |  | Decision | 2025-03-12 | 2025-03-20 | Not Started
T013 | User Acceptance Testing | Client reviews and approves website | Testing |  |  |  | 2025-03-18 | 2025-03-22 | Not started
T014 | Bug Fixing | Fix bugs identified during testing | Execution |  |  |  | 2025-03-20 | 2025-03-27 | Not Started
T015 | Security Check | Perform basic security checks | Testing |  |  |  | 2025-03-22 | 2025-03-28 | Not Started
T016 | Final Deployment Preparation | Prepare final deployment checklist | Close |  |  |  | 2025-03-25 | 2025-03-28 | Not Started
T017 | Project Handover | Handover project documents to client | Close |  |  |  | 2025-03-28 | 2025-03-31 | Not Started
Gantt Chart
[6 empty] | January |  |  |  |  | Feburary |  |  |  | March
Task ID | Task Name | Start Date | End Date | Days | Progress | 2025-01-01 | 2025-01-08 | 2025-01-15 | 2025-01-22 | 2025-01-29 | 2025-02-05 | 2025-02-12 | 2025-02-19 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-19 | 2025-03-26 | 2025-04-02
T001 | Requirement Gathering | 2025-01-01 | 2025-01-06 | 5 | 90%
T002 | Project Planning | 2025-01-08 | 2025-01-12 | 4 | 90%
T003 | UI/UX Design | 2025-01-13 | 2025-01-25 | 12 | 30%
T004 | Frontend Development | 2025-01-26 | 2025-02-15 | 20 | 90%
T005 | Backend Development | 2025-02-01 | 2025-02-28 | 27 | 27%
T006 | Testing | 2025-03-01 | 2025-03-15 | 14 | 13%
T007 | Deployment | 2025-03-20 | 2025-03-25 | 5 | 60%
T008 | Content Creation | 2025-02-10 | 2025-03-05 | 23 | 50%
T009 | Image & Media Collection | 2025-02-12 | 2025-02-28 | 16 | 10%
T010 | SEO Setup | 2025-03-05 | 2025-03-12 | 7 | 55%
T011 | Performance Optimization | 2025-03-10 | 2025-03-18 | 8 | 45%
T012 | Cross-Browser Testing | 2025-03-12 | 2025-03-20 | 8 | 50%
T013 | User Acceptance Testing | 2025-03-18 | 2025-03-22 | 4 | 70%
T014 | Bug Fixing | 2025-03-20 | 2025-03-27 | 7 | 35%
T015 | Security Check | 2025-03-22 | 2025-03-28 | 6 | 30%
T016 | Final Deployment Preparation | 2025-03-25 | 2025-03-28 | 3 | 20%
T017 | Project Handover | 2025-03-28 | 2025-03-31 | 3 | 10%
[7 empty] | Progress made | Days
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To understand If the action is an action or an Issue

## Task Assignment & Progress Trac
Task ID | Task Name | Assigned Resource | Assigned Date | Week | % Completion | Status | Remarks
T001 | Requirement Gathering | Aman Verma | 2025-01-01 | Week 1 | 100% | Completed | Completed on time
T002 | Project Planning | Aman Verma | 2025-01-08 | Week 2 | 100% | Completed | Approved by client
T003 | UI/UX Design | Neha Singh | 2025-01-13 | Week 4 | 100% | Completed | Minor revisions done
T004 | Frontend Development | Rahul Mehta | 2025-01-26 | Week 6 | 70% | In Progress | Homepage completed
T005 | Backend Development | Pooja Iyer | 2025-02-01 | Week 6 | 60% | In Progress | Database structure ready
T006 | Testing | Karan Patel | 2025-03-01 | Week 8 | 0% | Not started | Not started yet
T007 | Deployment | Rahul Mehta | 2025-03-20 | Week 10 | 0% | Not Started | Scheduled for March
T008 | Content Creation | Raj | 2025-02-10 | Week 7 | 10% | In Progress | Waiting for ugc
T009 | Image & Media Collection | Simran | 2025-02-12 | Week 8 | 30% | In Progress | Images completed, Videos remaining
T010 | SEO Setup | Sumeet U | 2025-03-05 | Week 9 | 0% | Not started
T011 | Performance Optimization | Manali K | 2025-03-10 | Week 10 | 0% | Completed
T012 | Cross-Browser Testing | Manali K | 2025-03-12 | Week 10 | 0% | Not Started
T013 | User Acceptance Testing | Atharva N | 2025-03-18 | Week 11 | 0% | Not Started
T014 | Bug Fixing | Devika N | 2025-03-20 | Week 13 | 0% | Not Started
T015 | Security Check | Neha Singh | 2025-03-22 | Week 14 | 0% | Not Started
T016 | Final Deployment Preparation | Mandaar Rao | 2025-03-25 | Week 15 | 0% | Not started
T017 | Project Handover | Dilp Joshi | 2025-03-28 | Week 16 | 0% | Not Started

## Resource List
Resource ID | Resource Name | Role | Department | Availability
R001 | Aman Verma | Project Manager | Management | Full-time
R002 | Neha Singh | UI/UX Designer | Design | Full-time
R003 | Rahul Mehta | Frontend Developer | Development | Full-time
R004 | Pooja Iyer | Backend Developer | Development | Full-time
R005 | Karan Patel | QA Tester | Testing | Part-time
Cost Tracking
Task ID | Task Name | Planned Cost (£) | Actual Cost (£) | Payment Status
T001 | Requirement Gathering | 2000 | 1800 | Paid
T002 | Project Planning | 1500 | 1500 | Paid
T003 | UI/UX Design | 4000 | 4200 | Paid
T004 | Frontend Development | 6000 | 5500 | Pending
T005 | Backend Development | 7000 | 6800 | Paid
T006 | Testing | 2500 | 0 | Pending
T007 | Deployment | 2000 | 0 | Pending

## Risks
Sr no | Risk | Description | Severity | Probability | Mitigation
1 | User Acceptance Testing | Client feedback may require major changes at a late stage | Low | Medium | Conduct early review sessions with client and get sign-off at each milestone
2 | Bug Fixing | Critical bugs may take longer than planned to resolve | Medium | High | Prioritize bugs based on impact and allocate additional testing time

## Dashboard
Task ID | Task Name | Team | Assigned Resource | Start Date | End Date | Task Duration | Status | Overdue | Comments
T001 | Requirement Gathering | Business Analysis | Aman Verma | 2025-01-01 | 2025-01-07 | 6 | Completed | FALSE
T002 | Project Planning | Project Management | Aman Verma | 2025-01-08 | 2025-01-12 | 4 | Completed | FALSE
T003 | UI/UX Design | Design | Neha Singh | 2025-01-13 | 2025-01-25 | 12 | Completed | FALSE
T004 | Frontend Development | Frontend Development | Rahul Mehta | 2025-01-26 | 2025-02-15 | 20 | In Progress | TRUE
T005 | Backend Development | Backend Development | Pooja Iyer | 2025-02-01 | 2025-02-28 | 27 | In Progress | TRUE
T006 | Testing | Quality Assurance | Karan Patel | 2025-03-01 | 2025-03-15 | 14 | In Progress | TRUE
T007 | Deployment | DevOps | Rahul Mehta | 2025-03-20 | 2025-03-25 | 5 | Not Started | TRUE
T008 | Content Creation | Content & Marketing | Raj | 2025-02-10 | 2025-03-05 | 23 | In Progress | TRUE
T009 | Image & Media Collection | Creative | Simran | 2025-02-12 | 2025-02-28 | 16 | In Progress | TRUE
T010 | SEO Setup | Digital Marketing | Sumeet U | 2025-03-05 | 2025-03-12 | 7 | Not started | TRUE
T011 | Performance Optimization | Engineering | Manali K | 2025-03-10 | 2025-03-18 | 8 | Not Started | TRUE
T012 | Cross-Browser Testing | Quality Assurance | Manali K | 2025-03-12 | 2025-03-20 | 8 | Not Started | TRUE
T013 | User Acceptance Testing | Client / Stakeholder | Atharva N | 2025-03-18 | 2025-03-22 | 4 | Not Started | TRUE
T014 | Bug Fixing | Engineering | Devika N | 2025-03-20 | 2025-03-27 | 7 | Not Started | TRUE
T015 | Security Check | Security | Neha Singh | 2025-03-22 | 2025-03-28 | 6 | Not Started | TRUE
T016 | Final Deployment Preparation | DevOps | Mandaar Rao | 2025-03-25 | 2025-03-28 | 3 | Not Started | TRUE
T017 | Project Handover | Operations | Dilp Joshi | 2025-03-28 | 2025-03-31 | 3 | Not Started | TRUE
Formulas:
Overdue = AND(Table1[[#This Row],[Status]]<>"COMPLETED",Table1[[#This Row],[End Date]]<TODAY())
TASK MANAGER TRACKER
Total Tasks
Not Started
17
Not Started
9
5
9
3
In Progress
Not Started
Completed
Overdue
# of Task by Owner
# of Task by Team
14

## Support Sheet
Owners | Count | Team | Count | Progress | Count
|  |  |  | Completed | 3
Aman Verma | 2 | Business Analysis | 1 | In Progress | 5
Neha Singh | 2 | Project Management | 1 | Not Started | 9
Rahul Mehta | 2 | Design | 1 | Total | 17
Pooja Iyer | 1 | Frontend Development | 1
Karan Patel | 1 | Backend Development | 1 | Count | Overdue
Raj | 1 | Quality Assurance | 2
Simran | 1 | DevOps | 2 | Count | 14
Sumeet U | 1 | Content & Marketing | 1
Manali K | 2 | Creative | 1
Atharva N | 1 | Digital Marketing | 1
Devika N | 1 | Engineering | 2
Mandaar Rao | 1 | Client / Stakeholder | 1
Dilp Joshi | 1 | Security | 1
|  | Operations | 1